# Solution design document template

# Step 3: Outline the solution and plan

# 1. Document control

| Version | Date | Author | Change Description |
| --- | --- | --- | --- |
| v1.0 | April 26, 2026 | Business Analyst | Initial draft of the Strategic Solution Proposal including SWOT and SMART goals. |
| v1.1 | April 27, 2026 | Business Analyst | Integration of SAP GTS/SAC technical requirements and risk mitigation strategies. |
| v1.2 | April 28, 2026 | Project Lead | Finalized RACI matrix and high-level implementation roadmap for Executive review. |

# 2. Problem statement

Current situation:

- The U.S. government has imposed tariffs of 15% to 25% on imported manufacturing components, specifically semiconductors and steel casings.

- Key trading partners, including the European Union and China, have responded with reciprocal tariffs that affect U.S. exports.

- Our organization operates a global supply chain with production facilities primarily based in Asia, making it highly vulnerable to these tariff shifts.

- The current procurement process lacks digital visibility, leading to incomplete tracking of tariff-adjusted landed costs.

Business needs: Mitigate financial risks and preserve profit margins by reducing the impact of import duties on the landed cost per unit.

Re-evaluate and diversify sourcing strategies to decrease dependency on high-tariff regions.

Implement business analysis enhancements, such as SAP Analytics Cloud (SAC) dashboards, to gain real-time visibility into cost volatility.

Maintain global competitiveness and market share despite an increasingly protectionist trade environment.

Constraints: The supply chain realignment must be completed within a strict 90-day assessment and execution window.

The organization has limited short-term flexibility to change existing suppliers or modify production lines immediately.

Proposed changes must align with current global trade regulations to avoid legal risks and penalties.

Assumptions: Existing trade agreements, such as the USMCA for Mexico-based production, will remain stable during the 18-month transition phase.

The current SAP S/4HANA backbone is compatible with the required GTS and SAC system updates without requiring a full-scale overhaul.

Qualified alternative manufacturing partners in non-tariffed zones (e.g., Vietnam and Mexico) are available and capable of meeting technical standards.

Executive leadership will provide the necessary sponsorship and rapid decision-making authority to meet the 10-week implementation roadmap.

Based on the strategic documents and analysis, here is the structured Solution Overview for your design document:

### 3. Solution Overview

Solution Description: The solution is a Hybrid Supply Chain Resiliency Model designed to mitigate the financial impact of 15% to 25% tariffs by diversifying the physical sourcing footprint and enhancing digital visibility. The strategy focuses on transitioning the procurement of high-tariff components—specifically semiconductors and steel casings—to duty-free trade zones while deploying SAP-driven analytics to manage cost volatility in real-time.

Key Features and Capabilities:

- Feature/Capability 1: Strategic Sourcing Diversification

  - Transitioning 40% of production volume for high-tariff components to alternative manufacturing hubs in Vietnam and Mexico.

  - Leveraging trade agreements like the USMCA to bypass import duties on goods shipped to the U.S..

- Feature/Capability 2: Real-Time Landed Cost Analytics

  - Implementation of SAP Analytics Cloud (SAC) dashboards to monitor tariff intelligence and landed cost fluctuations.

  - Enabling proactive pricing adjustments to protect the organization's 35% gross margin target.

- Feature/Capability 3: Automated Trade Compliance

  - Deployment of SAP Global Trade Services (GTS) to automate tariff classification and gümrük compliance processes.

  - Ensuring accurate duty payments and reducing the risk of legal penalties or customs delays.

Design Principles and Guidelines:

- Resilience Over Rigidity: Shift from a single-source Asia-based dependency to a flexible "China + N" sourcing model to withstand geopolitical shocks.

- Data-Driven Decision Making: Every pricing and sourcing shift must be justified by real-time data from the integrated SAP ecosystem.

- Proactive Compliance: Trade regulations and tariff changes must be monitored continuously by the Legal and IT teams to ensure system alignment before costs escalate.

- Agile Governance: Utilize a cross-functional "War Room" task force to facilitate rapid decision-making and meet the strict 90-day realignment window.

# 4. Architecture diagram

# 5. Functional requirements

| ID | Requirement Description | Priority (High/Med/Low) |
| --- | --- | --- |

| FR-01 | Automate tariff classification and gümrük compliance processes by deploying SAP GTS.1 | High |
| --- | --- | --- |
| FR-02 | Implement SAP Analytics Cloud (SAC) dashboards to monitor real-time tariff intelligence and landed cost fluctuations.1 | High |
| FR-03 | Provide analytical capability to enable proactive pricing adjustments necessary to protect the organization's 35% gross margin target.1 | High |
| FR-04 | Systematically manage the transition of 40% of production volume to alternative manufacturing hubs in Vietnam and Mexico.1 | High |
| FR-05 | Ensure the system leverages existing trade agreement data (e.g., USMCA) to bypass import duties on eligible goods.1 | High |

# 6. Solution components

Application Components:

- SAP Global Trade Services (GTS): The central engine for automated customs management, HS code classification, and ensuring compliance with shifting international trade regulations.

- SAP S/4HANA Procurement (MM): Responsible for managing the "Sourcing Logic," onboarding new suppliers in Vietnam and Mexico, and executing purchase orders under optimized trade terms.

- SAP Analytics Cloud (SAC): The primary platform for data stories, predictive modeling, and real-time visualization of financial impacts caused by tariff fluctuations.

- SAP Extended Warehouse Management (EWM): Manages inventory positioning within duty-free zones and bonded warehouses to defer or reduce tax liabilities.

Data Components:

- External Trade Intelligence Feed: API-driven data streams providing real-time updates on global tariff rates, duty draw-backs, and geopolitical trade shifts.

- Integrated Landed Cost Data Model: A unified data structure that combines base product costs with dynamic variables such as freight, insurance, and the 15%–25% tariff adjustments.

- Supplier Risk & Performance Metadata: Real-time data sets tracking the reliability and lead-time stability of new sourcing hubs in Southeast Asia and North America.

Infrastructure Components:

- SAP Business Technology Platform (SAP BTP): The integration layer that orchestrates secure data flow between the S/4HANA core, GTS compliance, and SAC analytics.

- Cloud Connector: A secure link ensuring seamless and encrypted communication between on-premise data environments and the SAP cloud ecosystem.

- Scalable Cloud Infrastructure: High-availability server environment designed to handle large-scale data processing for global supply chain simulations.

User Interfaces:

- Executive War Room Dashboard: A high-level SAC interface providing the "Single Source of Truth" for leadership to monitor gross margin health and strategic pivots.

- Margin-at-Risk Simulator: An interactive tool for pricing analysts to model "What-if" scenarios and determine optimal price adjustments based on varying duty levels.

- Compliance & Logistics Monitor: An operational Fiori-based interface for trade specialists to track customs clearance status and documentation accuracy.

- Mobile Alert System: Real-time notifications for procurement officers regarding supply chain bottlenecks or sudden regulatory changes.