## put them in title case
Risk Description | Mitigation Strategy | Responsible Party | Contingency Plan | Risk Score
R001: Data Migration Complexity and Errors Leading to Data Integrity Issues across MM, WM, and SD modules. | 1. Conduct comprehensive data profiling and cleansing in legacy systems. 2. Execute multiple Mock Cutover cycles to validate transformation rules. 3. Implement automated data validation scripts during the ETL process. | Data Migration Team / IT Project Lead | Develop a detailed Data Rollback Plan and establish a manual reconciliation team to address post-load anomalies.
R002: Lack of User Adoption Due to Inadequate Training and Resistance to Change in new SAP S/4HANA workflows. | 1. Establish a Change Champion network from key business units. 2. Develop a multi-tiered training program (E-learning and Sandbox practice). 3. Engage end-users early in the UAT phase. | Change Management Lead / Training Department | Deploy a Hypercare support model post-go-live with on-site floor walkers and continuous feedback optimization loops.
Appendix: Risk Assessment Data
Risk Id | Risk Description | Likelihood | Impact | Risk Score
R001 | Data Migration Complexity And Errors Leading To Data Integrity Issues | High | High | High
R002 | Lack Of User Adoption Due To Inadequate Training And Resistance To Change | Medium | High | High
R003 | Integration Issues With Existing Third-Party Logistics And Customer Systems | Medium | Medium | Medium
R004 | Budget Overruns Due To Unforeseen Customization Requirements And Scope Creep | Low | High | Medium
R005 | Project Delays Due To Resource Constraints And Unavailability Of Key Personnel | Medium | Medium | Medium

## Risk Register
Risk Id | Risk Description | Likelihood | Impact | Risk Score
R001 | Data Migration Complexity And Errors Leading To Data Integrity Issues | High | High | High
R002 | Lack Of User Adoption Due To Inadequate Training And Resistance To Change | Medium | High | High
R003 | Integration Issues With Existing Third-Party Logistics And Customer Systems | Medium | Medium | Medium
R004 | Budget Overruns Due To Unforeseen Customization Requirements And Scope Creep | Low | High | Medium
R005 | Project Delays Due To Resource Constraints And Unavailability Of Key Personnel | Medium | Medium | Medium