Project Template: Change Strategy Outline for Project Unity

Instructions: Fill in each section below based on your analysis of the Project Unity scenario provided in the activity. Be concise and focus on the key points as guided by the activity tasks.

A. Project Goal & Change Summary:

- Project Goal: (Write 1 sentence stating the main business goal of Project Unity, e.g., "Improve efficiency and control via SAP FI/CO & MM implementation")

  - Improve operational efficiency and financial control by implementing SAP S/4HANA (FI/CO and MM modules) to reduce month-end closing from 10 to 5 days and achieve a 15% reduction in procurement costs.

- Core Change for Employees: (Write 1 sentence summarizing the fundamental change for employees, e.g., "This involves replacing familiar legacy systems and manual processes with standardized SAP workflows")

  - This involves replacing 15-year-old legacy systems and manual Excel-based processes with standardized SAP workflows, requiring a shift from siloed tasks to integrated digital operations.

B. Key Stakeholders & Primary Concerns:

(List the 3 priority stakeholder groups identified in Task 1b and their primary concern from Task 1c)

- Stakeholder Group: Finance Department

  - Primary Concern: Fear of job redundancy due to SAP’s automation capabilities and the loss of familiar, customized Excel reporting formats.

- Stakeholder Group: Procurement Department

  - Primary Concern: Anxiety regarding the perceived complexity of the SAP interface ("too many clicks") and fear that standardized system processes won't capture the nuances of specialized raw material sourcing.

- Stakeholder Group: Warehouse Staff

  - Primary Concern: Lack of clarity and communication regarding how the SAP MM integration will change their daily workflow with handheld scanners and WMS interface.

C. Top Change Risks & Mitigation/Communication Strategies:

(List the 2 top risks identified in Task 1d and the corresponding strategies developed in Task 2)

- Risk: Widespread resistance within the Finance department leading to low participation in design workshops and failure to adopt the new 5-day closing process.

  - Mitigation Action(s): Conduct "Future-State Role Mapping" workshops to demonstrate how automation eliminates data entry but creates "Analyst" roles. Include resistant Finance users as "Process Testers" to give them a sense of ownership.

  - Associated Communication Strategy:

    - Who: Finance Department users and Department Head.

    - Key Message: "SAP is a tool for empowerment, not replacement; we are moving from manual entry to strategic financial analysis."

    - Channel/Method: In-person town hall led by the CFO followed by hands-on demo sessions showing "A Day in the Life" with SAP.

    - Owner (Conceptual): Change Manager & CFO.

- Risk: Procurement team’s struggle with system complexity causes a significant drop in productivity and damages long-term supplier relationships during the transition.

  - Mitigation Action(s): Launch a "Procurement Super User" program involving the most vocal skeptics to co-design the Fiori (simplified) interface. Develop specialized "Supplier Transition Support" protocols to ensure no order bottlenecks.

  - Associated Communication Strategy:

    - Who: Procurement Department team and Warehouse Managers.

    - Key Message: "We are simplifying the 'clicks' to focus on supplier quality; your expertise is what drives the system, not the other way around."

    - Channel/Method: Weekly department huddles and easy-access "Quick Reference Guides" (QRGs) tailored to their specific sourcing tasks.

    - Owner (Conceptual): Procurement Head & Change Manager.

D. Key Training & Support Needs Summary:

(Summarize the 1-2 most critical needs identified in Task 3)

- Critical Need: Mandatory, role-specific "Closing & Sourcing Simulation" training delivered 4-6 weeks before go-live. This must focus on end-to-end scenarios (e.g., PO-to-Payment) rather than just individual transactions to break down departmental silos.

- Essential Support: A dedicated "Hypercare Taskforce" consisting of BT specialists and departmental Super Users stationed physically in the Finance and Warehouse areas for the first 30 days post-go-live to provide immediate, floor-level troubleshooting.