## Project Tracker
Objective | Initiative | Start Date | End Date | Department | Manager | Status | Progress(%) | Visual | Comments | Dependencies
Enhnance Customer Experience: Reduce customer support response time by 20% | Implement customer feedback portal: Launch by Q2 2026 | 2025-01-04 | 2026-01-04 | Customer Support | Jane Doe | Planning | 10 |  | Kick off meeting set for next week, awaiting vendor contract approval | IT infrastructure setup
Streamline Internal Processes | Reduce manuel effort in sales order creation | 1/16/2025 | 7/31/2025 | Sales | Bruce Banner | In Progress | 50 |  | IT installing automation componenet | SAP note installation
Deveolp New Product Line | Expand into automative industry | 2024-01-01 | 2025-01-05 | Sales | Bruce Banner | Completed | 100 |  | New product launched ahead of schedule | N/A
Enhance Employeee Training | Develop eLearnings and Instructor-led trainings | 2025-05-02 | 2025-01-10 | Operations | Barry Alan | Planning | 15 |  | Contracting issues need to be resolved before continuing | Contract negotiation

## Project Overview
Total Number of Projects | 4
Not Started | 0
Planning | 2
In Progress | 1
Completed | 1
Blocked | 0